## Event
Line | Plan | Actual | Variance | Note
Venue | 18000 | 18000 | 0 | Community hall, paid
Food | 12000 | 13500 | 1500 | Forty plates, price increased
Drinks | 3000 | 2800 | -200 | Under plan
Photos | 4000 | 4500 | 500 | Extra hour
Decor | 2500 | 2500 | 0 | On plan
Contingency | 5500 | 5550 | 50 | Used for the food gap and a small extra
Total | 45000 | 46850 | 1850 | Variance above zero means over plan